# Smart Parking Platform Project Management

### PREPARED FOR

$oftware ¢orp

### PREPARED BY

Stephanie Martinez

# Homework 5

# Roles & Resources

| Team Member | Project Role | Skill Level | Main Responsibilities | Allocation % |
| --- | --- | --- | --- | --- |
| Elena Ramirez | Project Manager | Senior, 10+ years | Schedule, budget, risks, stakeholder coordination, sprint oversight, vendor/API coordination | 75% |
| Marcus Lee | Business Analyst/ Product Owner | Senior, 7+ years | Requirements, backlog, user stories, acceptance criteria, stakeholder interviews | 51% |
| Sofia Patel | UX/UI Designer | Senior, 6+ years | Driver and operator UX, wireframes, prototypes, responsive interface design | 38.5% |
| Daniel Kim | Mobile Developer | Senior, 7 years | iOS/Android driver application, notifications, parking workflows | 70% |
| Priya Shah | Mobile Developer | Mid/Senior, 5 years | Mobile UI, authentication, vehicle registration, payments | 70% |
| Jordan Brooks | Web Developer | Senior, 7 years | Driver web application and responsive web architecture | 70% |
| Luis Hernandez | Web Developer | Mid-level, 5 years | Operator dashboard, reporting UI, account management | 70% |
| Omar Hassan | Backend/API Lead | Senior, 10 years | System architecture, APIs, parking-session logic, availability engine | 85% |
| Maya Chen | Backend Developer | Senior, 8 years | Database logic, account services, reporting APIs, synchronization | 85% |
| Nina Alvarez | Mapping & Location Engineer | Senior, 7 years | Garage location, maps, navigation APIs, proximity search | 40% |
| Victor Nguyen | Payment Integration Engineer | Senior, 8 years | Payment gateway, wallets, transaction security, receipts/refunds | 30% |
| Grace Wilson | QA/Test Engineer | Senior, 7 years | Functional, integration, regression and cross-platform testing | 60% |
| Ethan Park | QA/Test Engineer | Mid-level, 5 years | Mobile/web testing, test cases, defect verification | 60% |
| Noah Thompson | DevOps/Cloud Engineer | Senior, 8 years | CI/CD, cloud infrastructure, environments, monitoring, deployment | 50% |
| Aisha Rahman | Security & Privacy Engineer | Senior, 9 years | Authentication security, payment/security review, privacy, access control | 43.5% |
| Chloe Martin | Technical Writer/ Training Specialist | Mid-level, 5 years | System documentation, operator guides, deployment/training materials | 20% |

# Resource & Cost Plan

We decided to go with a bottom-up estimate, which calculates the cost of each individual resource and component, then adds them together to determine the total project budget. Additionally, we based cost within Texas paid salaries:

### A. Labor Cost Plan:

| Job | Category | Quantity (Hrs) | Unit Cost | Duration | Total |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Labor | 1,200 hrs | $85/hr | 10 months | $102,000 |
| Business Analyst/ Product Owner | Labor | 816 hrs | $70/hr | 10 months | $57,120 |
| UX/UI Designer | Labor | 616 hrs | $65/hr | 8 months active | $40,040 |
| Mobile Developers – 2 | Labor | 2,240 hrs | $70/hr | ~9 months active | $156,800 |
| Web Developers – 2 | Labor | 2,240 hrs | $65/hr | ~9 months active | $145,600 |
| Backend/API Developers – 2 | Labor | 2,720 hrs | $80/hr | 10 months | $217,600 |
| Mapping & Location Engineer | Labor | 640 hrs | $80/hr | ~8 months active | $51,200 |
| Payment Integration Engineer | Labor | 480 hrs | $85/hr | ~6 months active | $40,800 |
| QA/Test Engineers – 2 | Labor | 1,920 hrs | $55/hr | ~8 months active | $105,600 |
| DevOps / Cloud Engineer | Labor | 800 hrs | $80/hr | 10 months | $64,000 |
| Security & Privacy Engineer | Labor | 696 hrs | $90/hr | 10 months | $62,640 |
| Technical Writer / Training | Labor | 320 hrs | $50/hr | 4 months active | $16,000 |
| Total Labor |  |  |  |  | $1,059,400 |

### B. Infrastructure, Tools & Integration Costs

| Item | Category | Qty (Months) | Unit Cost/ Basis | Duration | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Cloud hosting & environments | Infrastructure | 10 months | Variable usage | 10 | $80,000 | Development, staging, testing and production |
| Mapping/location API services | Infrastructure/ API | 10 months | Usage- based | 10 | $54,500 | Garage search, geolocation, routing/navigation |
| Development & QA licenses | Tools | Project team | Blended | 10 | $24,000 | IDEs, design, testing, monitoring tools |
| Security/privacy testing | Security | Project | Specialized services/ tools | N/A | $35,000 | Vulnerability, penetration and privacy testing |
| Test devices & garage integration equipment | Hardware | Project | One-time | N/A | $30,000 | Phones, tablets, access-control integration test equipment |
| Pilot garage/access control integration | Infrastructure | Pilot | One-time | Final phases | $50,000 | Gate/access testing and garage pilot equipment |
| Total non-Labor |  |  |  |  | $273,500 |  |

### Base project subtotal

- Labor: $1,059,400

- Infrastructure/tools/integration: $273,500

- Base cost: $1,332,900

- Contingency reserve: 10%

### Total Estimated Project Budget: $1,466,190

# RACI matrix

### Legend:

R — Responsible: performs the work.

A — Accountable: ultimately owns the result and approves it.

C — Consulted: provides expertise or feedback.

I — Informed: receives progress/results.

| Task / Role | PM | BA/ Product Owner | UX/UI | Development Teams | Mapping/Payment Specialists | QA | DevOps / Security |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering | A | R | C | C | C | C | I |
| Product Backlog/ User Stories | A | R | C | C | C | C | I |
| System Architecture | C | C | I | A/R | C | C | C |
| Driver & Operator UI Design | A | C | R | C | I | C | I |
| Authentication & Account System | I | C | C | A/R | I | C | C |
| Vehicle Registration Development | I | C | C | A/R | I | C | C |
| Parking Availability Engine | I | C | C | A/R | C | C | C |
| Parking Reservation System | I | C | C | A/R | C | C | C |
| Map & Navigation Integration | I | C | C | C | A/R | C | C |
| Payment Processing Integration | I | C | C | C | A/R | C | C |
| Transparent Pricing/ Fee Calculation | C | C | C | R | A | C | I |
| Operator Dashboard | I | C | C | A/R | I | C | I |
| Reporting & Analytics | I | C | C | A/R | I | C | I |
| Notifications & Alerts | I | C | C | A/R | C | C | C |
| Security & Privacy Compliance | I | C | I | C | C | C | A/R |
| Functional Testing | I | C | I | C | I | A/R | C |
| Integration Testing | I | I | I | C | C | A/R | C |
| Performance Testing | I | I | I | C | I | R | A |
| User Acceptance Testing | A | R | C | C | I | R | I |
| Defect Resolution | I | I | I | A/R | R (where applicable) | C | C |
| Production Deployment | A | I | I | C | I | C | R |
| Operator Training & Documentation | A | C | C | C | I | C | R* |
| Project Closure & Final Acceptance | A/R | C | I | I | I | C | I |